## Staff
|  |  |  | Assign to | Date Completed | Status
Staff
Has the Camp Director been idenitified?
Schedule the Camp Director's Camp Training with the BSA, if required.
|  | BSA National Camping Calendar | https://www.ncsbsa.org/calendar/
Have staff and volunteers been identified and confirmed?
Has the Council staff been contacted to establish communication of the event?
| Who from Council will be available during the day of the event? |  |  |  |  | Council will be there. Cynthia and Emily

## Administration
Twilight Camp Event Planner
Camp Name |  | Potawatomi Cub Scout Twilight Camp
Date |  | June 1 - 3, 2016
Time |  | 3:30pm - 8:00pm Central Standard Time
Location |  | Crow Island Woods, 1140 Willow Rd, Winnetka, IL 60093
Primary points of contact |  | David Schwartzberg | m: 847.414.4507
Karen Pinelli
Target participants |  | For Tiger Scouts (Kindergarten boys who will be 1st graders in September), Wolf & Bear Scouts, and Webelos.
Who is this event targeted at?
What does the participants need to know?
What will hold their interest?
Message
What do you want to say to the target audience?
What do you want them to know/do?
Objectives
Describe the value each scout is expected to receive from attending camp.
Description
Include the objective in the description, but expand upon the objective to motivate a parent to register their scout for Twlight Camp. Incorporate the theme into your flyers and promotions. Sell it!
Risk assessment
Identify where risk will exist and potentially exist. Strategize on how to address the identified risks. For example: plan to have a First Aid station.
Risk reduction/mitigation options
Assign an experienced scouting volunteer as risk mitigation officier during the planning stage.
Evaluation Criteria Benchmarks
What were our aims/objectives?
Did we achieve what we set out to do?
Did it come in on budget?
What were the intended/unintended outcomes?
How do we measure effectiveness?
What tools do we use to measure our success?
|  |  |  | Assign to | Date Completed | Status
Venue
|  | Has the venue been reserved, including the day prior to the event for setup? Deposits paid? |  | David Schwartzberg | May 1st | Done
|  | What permits are required? |  | Karen Pinelli |  | Completed request, no permits required
|  | How far in advance do the permits need to be filed? |  | N/A
|  | Do any staff require training prior to the event taking place in regards to the venue and permits? |  | David Schwartzberg |  | Camp Training approved by Council;
Camp Registration
|  | Select a date to have Twilight Camp. That date will be dependant upon venue availability. |  | Council |  | Dates June 1 - 3, 2016 selected
|  | Decide how registration will be processed. Ideally, visa vie the Council web site. |  | Karen Pinelli |  | Discussed between KP and DS
|  | What information will be required and considered optional during registration? |  | Karen Pinelli
|  | Payment should be online at the end of registration to ensure camp check-in is expeditious. |  | Karen Pinelli
|  | Medical forms A and B will be required. Communicate and distribute the medical forms 4 weeks prior to camp check-in. During camp, be prepared with blank medical forms, registration forms and any additional required forms. |  | Karen Pinelli
|  | Registration identifier? |  | Karen Pinelli | May 8th | Wrisbands provided by Cynthia C.
Training
|  | Have the Camp Director and Program Director completed Camp School Training? |  | David Schwartzberg | 2/29/2016 | Registered; Camp Training approved by Council
|  |  |  | Darryl Nishibun | 2/29/2016 | Registered; Camp Training approved by Council

## Meals
|  | Assign to | Date Completed | Status
Mess Detail
| Who's Head Chef? | Tim Rueckert
Will permits be required?
Will the town/village/city food inspectors need to be notified?
Define a budget on food for all days.
Head Chef needs to write a menu within budget.
Does the menu need to be reviewed by a Nutrionist? If so, is there already someone on staff or does staff known someone?
Have dietary restrictions been requested during the registration process?
Did the menu account for dietary restrictions?
Deadline for when a shopping list is written based on menu.
Define who will help the Head Chef with the shopping.
Where will the food be purchased? Do they waive taxes for 501(c)(3) charities?
Who will be helping the Head Chef before, during, and after the event?
What equipment will be needed?
Who will be keeping inventory of equipment before and after event?
Plan for rain and other risks that would adversly impact the Mess area.
Do you have prior year receipts to plan for current year?

## Activities
[6 empty] | Assign to | Date Completed | Status
Daily Opening Ceremony
Does the venue have an existing flag pole? If not, consider alternatives.
Assign the boy scout den leaders to provide a pre-camp activity during check-in.
How will the opening ceremonies begin?
Will all scouts presenting the colors and retiring the colors be in Class A uniforms?
Activities
| Who is the Program Director? |  |  |  | Daryl Nishibun |  | Confirmed on 2/1/2016
| Who is the Asst Program Director? |  |  |  | Chris Lowery |  | Confirmed 2/8/2016
| Has a theme been selected? |  |  |  | Yes, CSI - Cub Scout Investigators
| Who will create the theme based flyer? |  |  |  | Yes, created by Council
How can the Council provide additional assitance and support with artwork design, flyer creation and promotion?
Which activities will be available? (Keep to ~10 activities)
|  | Activity | Staff | Required Equipment / Supplies
| 1 | Climbing Wall | Chuck Pint, Paul Pint +1 more | Rock Wall from Okarro and harnesses, certified personnel
| 2 | Arts and Crafts | Mary Wadleigh and Beth | Depends upon craft
| 3 | Rope Bridge | Larry young +1 more | Rope Bridge, support beams, table, safety equipment, alligator
| 4 | Water Bottle Rockets | Chris Hersee & Pete Hall | Water, Hose, Air pumps, Bottles, Launchers
| 5 | Sport | TBD | Review past 2 years so don’t repeat
| 6 | Slingshots | TBD | Sling Shots (Oakarro), beans, targets, tarp, bean holder
| 7 | Archery | Cleland Noe? +3 other staff | Targets, Stands, Bows, Arrows, Tarps, Stakes, Tape, Forearm and finger guards – Need Certified Instructor (Cleland Noe?, Saigo?)
| 8 | STEM | Patrick Z | TBD
| 9 | Beep Ball | Jim Capek | Beep ball equipment
| 10 | TBD | TBD | TBD
Has the staff assigned to the activity been confirmed?
Has the equipment and supplies for the activities been identified and reserved?
Use a to scale map of the venue and determine where each activity will be held.

## Campfire
|  | Assign to | Date Completed | Status
Camp Fire
Does the venue selected allow camp fires?
Is a permit required to have a campe fire at the venue?
Has the local Fire Marshall been notified about the camp fire, if required?
Who will lead the camp fire?
Will there be skits / songs / jokes performed by the scouts?
Do you want to have a flag retirement ceremony?
How will the logs be setup?
Who will start the fire?
Who will properly extinguish the fire?

## First Aid
|  | Assign to | Date Completed | Status
First Aid
Health officer assigned?
Backup health officers
Have a daily health log kept accurate for insurance.
Determine the necessary equipment for the First Aid area (ie pop-up tent, cots, ice coolers, etc)
Confirm that all CPR/AED and required certifications are current.
Ensure the medical staff have access to the contact's list of the scouts.